## Slide 1
OVERSIGHT REPORT
Paul E. Joseph
Stadium & Sports Complex
A Contractual, Financial & Timeline Review
July 2025 — April 2026
PREPARED FOR
Senator-at-Large
Angel Bolques Jr.
36th Legislature of the Virgin Islands

## Slide 2
01
EXECUTIVE SUMMARY
The Record Speaks Plainly
On August 5, 2025, the Department of Public Works confirmed to this Committee that the Paul E. Joseph Stadium would be completed by December 25, 2025. The contract record tells a different story.
Based on Several Change Orders
5
CHANGE ORDERS
Approved June 2025 – April 2026
554+
CALENDAR DAYS ADDED
Cumulative time extensions
$557K
DISBURSED
July 2025 – January 2026
Jul 2, 2026
CURRENT TARGET
Per Change Order No. 10
The project was not completed by December 25, 2025. It was extended, funded, and actively executed into 2026.
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
2 / 20

## Slide 3
02
THE REPRESENTATION
What the Office Was Told
AUGUST 5, 2025
“The project remains on track for completion by December 25, 2025.”
— John Wessel and Derek A. Gabriel
Commissioner, Department of Public Works
THE PROBLEM
This assurance was given six weeks after a 180-day extension had already been approved on the same contract.
THE CONTRACT RECORD SHOWS
June 27, 2025 — Change Order No. 1 approved, adding 180 days to Supplemental Contract No. 2.
August 5, 2025 — DPW nevertheless confirmed December 25, 2025 as the completion date to this Committee
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
3 / 20

## Slide 4
03
FINANCIAL SNAPSHOT
Funding Report — As of January 31, 2026
Source: Virgin Islands Public Finance Authority, letter dated January 31, 2026
$32.45M
TOTAL BUDGET
$26.35M
EXPENDED
$6.10M
AVAILABLE
FUNDING SOURCES
Funding Source | Budget | Expended | Available | Authorization
Series 2003 Gross Receipt Tax Bonds | $1,150,000 | $1,150,000 | $0 | Bd. Res. 03-013 & 15-012
Series 2014C Gross Receipt Tax Bonds | $17,500,000 | $17,453,163 | $46,837 | Act 7453, Sec. 2(D)
Community Facilities Trust Account | $480,000 | $282,187 | $197,813 | Acts 7990 & 8009
Community Facilities Trust Account | $5,124,000 | $902,025 | $4,221,975 | Act 8781, Sec. 1
Internal Revenue Matching Fund | $8,200,000 | $6,566,679 | $1,633,321 | Act 8326, Sec. 1
TOTALS | $32,454,000 | $26,354,054 | $6,099,946 | 
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
4 / 20

## Slide 5
04
SCOPE EXPANSION
A Project That Grew in Cost and Scope
The PEJ Project is not simply one delayed contract. It is an original award expanded by two supplemental contracts that together added more than $9.2 million and introduced additional timelines, parties, and payment flows.
ORIGINAL CONTRACT
~$20.0M
Design/Build — Paul E. Joseph Stadium & Sports Complex
SUPPLEMENTAL CONTRACT NO. 1
$4.10M
C003ASPRC15 — GEC, LLC (Additional Work)
SUPPLEMENTAL CONTRACT NO. 2
$5.12M
PO-24-810-8102-688 — GEC, LLC (Additional Work)
FINDING
The project did not merely slip its schedule — it grew. Two supplemental contracts added roughly $9.22M and created parallel timelines that are now extended independently through separate change orders.
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
5 / 20

## Slide 6
01
BEFORE THE REPRESENTATION
Change Order No. 1 — June 27, 2025
SUPPLEMENTAL CONTRACT NO. 2
+180
CALENDAR DAYS ADDED
COMMENCEMENT
June 29, 2025
NEW COMPLETION
December 25, 2025
CONTRACT VALUE
$5,124,000 (unchanged)
APPROVED BY
DPW / DSPR / DPP
REASON CITED
“Increase in contract time by 180 calendar days to allow for additional time to complete the project.”
SIGNIFICANCE
By the time this Committee was told on July 18, 2025, that the stadium was on track for December 25, 2025, a 180-day extension had already been formally approved on this very contract six weeks earlier. The December 25, 2025, date was itself the product of an extension.
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
6 / 20

## Slide 7
02
EXTENDED BEFORE DEADLINE
Change Order No. 2 — December 23, 2025
SUPPLEMENTAL CONTRACT NO. 2
+96
CALENDAR DAYS ADDED
COMMENCEMENT
December 26, 2025
NEW COMPLETION
April 1, 2026
CONTRACT VALUE
$5,124,000 (unchanged)
APPROVED BY
DPW / DSPR / DPP
REASON CITED
“Increase in contract time by 96 calendar days to allow for additional time to complete the project.”
SIGNIFICANCE
Approved on December 23, 2025 — two days before the contract was supposedly to be complete. This is the first formal, written break from the December 25, 2025 completion date DPW confirmed to the Office in August.
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
7 / 20

## Slide 8
03
THE ADMINISTRATIVE ADMISSION
Change Order No. 9 — December 23, 2025
CONTRACT C003ASPRC15 — GEC, $4.1M
+96
CALENDAR DAYS ADDED
COMMENCEMENT
December 26, 2025
NEW COMPLETION
March 31, 2026 / April 1, 2026
CONTRACT VALUE
$4,100,000 (unchanged)
APPROVED BY
DPW / DSPR / DPP
REASON CITED
“...to allow the Government to pay Contractor’s Subcontractors and/or Vendors via electronic payments, rather than joint payments, in order to expedite payments...”
SIGNIFICANCE
This change order admits, in writing, that part of the delay is tied to Government payment operations — not only contractor performance. Delay is now officially linked to administrative and financial processes within the Executive Branch.
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
8 / 20

## Slide 9
04
PAST THE REVISED DEADLINE
Change Order No. 3 — April 14, 2026
SUPPLEMENTAL CONTRACT NO. 2
+91
CALENDAR DAYS ADDED
COMMENCEMENT
April 2, 2026
NEW COMPLETION
July 2, 2026
CONTRACT VALUE
$5,124,000 (unchanged)
APPROVED BY
DPW / DSPR / DPP
REASON CITED
“Increase in contract time by 91 calendar days to allow for additional time to complete the project.”
SIGNIFICANCE
Approved thirteen days after the April 1, 2026 completion date itself had passed. The project was not complete on its second revised deadline either. The justification again references payments to subcontractors and vendors.
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
9 / 20

## Slide 10
05
THE CURRENT POSITION
Change Order No. 10 — April 14, 2026
CONTRACT C003ASPRC15 — GEC, $4.1M
+91
CALENDAR DAYS ADDED
COMMENCEMENT
April 2, 2026
NEW COMPLETION
July 2, 2026
CONTRACT VALUE
$4,100,000 (unchanged)
APPROVED BY
DPW / DSPR / DPP
REASON CITED
“Increase in contract time by 91 calendar days to allow for additional time to complete the project.”
SIGNIFICANCE
This is the current contractual target. July 2, 2026 is now more than six months past the date DPW represented to the Office in August 2025 — and there is no contractual guarantee it will be the last extension.
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
10 / 20

## Slide 11
10
CUMULATIVE DELAY
Days Added to Complete the Stadium
TOTAL DAYS ADDED
554
calendar days (≈ 18 months)
Across five approved change orders
June 2025 — April 2026
Chart: Calendar Days Added Per Change Order
| CO No. 1 Jun 2025 | CO No. 2 Dec 2025 | CO No. 9 Dec 2025 | CO No. 3 Apr 2026 | CO No. 10 Apr 2026
Days Added | 180 | 96 | 96 | 91 | 91
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
11 / 20

## Slide 12
11
PROJECT TIMELINE
Representation vs. Reality
June 27, 2025
CO #1: +180 days
Aug 5, 2025
DPW: “On track Dec 25”
Dec 23, 2025
COs #2 & #9: +192
Dec 25, 2025
Promised Completion
Apr 14, 2026
COs #3 & #10: +182
Jul 2, 2026
Current Target
Each red marker is a promise. Each gold marker is an extension. The pattern is visible.
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
12 / 20

## Slide 13
12
FOLLOW THE MONEY
Payments Continued Through the Delay
Disbursement activity from July 2025 through January 2026 confirms the project was not paused, mothballed, or idle. It was actively funded across the same months the completion timeline was slipping.
TOTAL DISBURSED
$557,091
July 2025 — January 2026
Across the prime contractor, the Government, and at least five vendors/subcontractors.
Chart: Where the Money Went
| GEC, LLC (Prime) | VI Bureau of Internal Revenue | Vendors & Subcontractors
Disbursements | 371655 | 27855 | 157582
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
13 / 20

## Slide 14
13
PAYMENT BREAKDOWN
Who Was Paid, and When
PRIME CONTRACTOR
GEC, LLC
$371,655
07/23/2025 — $55,361.25
07/31/2025 — $69,852.71
07/31/2025 — $134,577.00
09/30/2025 — $10,281.38
09/30/2025 — $21,754.10
11/13/2025 — $50,872.50
01/29/2026 — $24,699.04
SC PE #16 — $4,256.80
GOVERNMENT
VI Bureau of Internal Revenue
$27,855
07/23/2025 — $2,913.75
07/31/2025 — $3,676.46
07/31/2025 — $7,083.00
09/30/2025 — $541.13
09/30/2025 — $1,144.95
11/13/2025 — $2,677.50
01/29/2026 — $7,164.27
SC PE #16 — $2,653.54
VENDORS & SUBCONTRACTORS
Five Separate Entities
$157,582
Medley Steel & Supply — $33,087.90
Ferguson Enterprises — $55,737.81
Berls Commercial Supply — $21,459.02
Total Restrooms — $1,137.28
Bond Plumbing Supply — $46,160.41
(Materials flowing onto the site
after the Dec. 25 promise date.)
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
14 / 20

## Slide 15
14
THE JANUARY 2026 EVIDENCE
Still Building, One Month After
the “Completion” Date
January 29, 2026
$143,000+
paid in a single disbursement cycle — more than one month after the promised December 25, 2025 completion date.
PROJECT ACTIVE
Funds flowing to the prime contractor
MATERIALS MOVING
Vendors engaged, invoices processed
NOT COMPLETE
A finished stadium does not need fresh pay cycles
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
15 / 20

## Slide 16
15
CONTRACTUAL ACCOUNTABILITY
Liquidated Damages: A Provision Never Triggered
CONTRACT PROVISION
$500
per day | liquidated damages
Under Contract C003ASPRC15, liquidated damages of $500 per day are available to the Government for failure to meet substantial completion deadlines. Damages may be deducted from payments or collected by the Government.
OVERSIGHT CONCERN
Because each missed deadline has been followed by an approved time extension, liquidated damages have not been triggered.
NO DISTINCTION
Change orders do not document whether delays are excusable or non-excusable.
NO EVALUATION
No record indicates whether liquidated damages were ever assessed before extensions were granted.
NO ENFORCEMENT
Repeated extensions have effectively reset deadlines and prevented enforcement.
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
16 / 20

## Slide 17
16
BARRIERS TO OVERSIGHT
Information and Access
Legislative oversight of this project has been repeatedly delayed — not by disagreement, but by the pace of responses and the absence of confirmed site access.
INFORMATION FLOW
Updates promised “in a few weeks”
Requests for project schedules, progress report updates, and revised completion dates were made but responses have been limited. DPW indicated no further replies would follow until the promised update was ready.
SITE ACCESS
Requested Aug 2025 • Re-requested Feb 2026
A site visit referenced back to August 2025 was re-requested in February 2026. DPW indicated coordination ongoing and a tentative March visit, but no date has been confirmed in the record.
DOCUMENTARY RELIANCE
1,000+ pages produced by contractor
The investigative record is heavily supported by contractor-submitted materials (GEC). The majority of detailed schedules, timelines, and internal tracking come from the contractor rather than the agency.
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
17 / 20

## Slide 18
17
FINDINGS
Five Findings the Record Supports
01
TIMELINE DISCREPANCY
Publicly represented completion (Dec 25, 2025) diverges from internal contract record, which projects completion into July 2026.
02
EXTENSIONS APPROVED EARLY
Change orders dated Dec 23, 2025 were approved two days before the represented completion date itself arrived.
03
CONTINUED FINANCIAL ACTIVITY AMIDST UNDERPERFORMANCE OF CONTRACTOR
More than $557,000 disbursed July 2025 – January 2026, including a $143K+ single cycle after the promised deadline.
04
ADMINISTRATIVE DELAYS
Change Orders No. 9 and No. 3 cite Government payment processing as a contributing cause of delay.
05
ACCOUNTABILITY MECHANISM DORMANT
$500/day liquidated damages provision exists in the contract but has not been triggered; extensions effectively reset the deadline each time.
PAUL E. JOSEPH STADIUM | OVERSIGHT REPORT
18 / 20

## Slide 19
18
CONCLUSION
The Bottom Line
The project was not completed by December 25, 2025, and the record shows a troubling pattern of missed deadlines, last-minute extensions that shifted responsibility instead of enforcing it, and continued payments despite clear underperformance. At the same time, the accountability measures already written into the contract were never enforced, allowing delays to continue without consequence or penalties.
Five change orders • 554 days added • $557K disbursed • $500/day damages unenforced
The record does not speculate — it documents.

## Slide 20
OFFICE OF
Senator-at-Large
Angel Bolques Jr.
36th LEGISLATURE | VIRGIN ISLANDS
Paul E. Joseph Stadium Oversight Report
Record compiled from contractual, financial, and legislative correspondence — July 2025 through April 2026.