## Slide 1: OFFICE OF DISASTER RECOVERY
Committee on Disaster Recovery, Infrastructure, and Planning
April 24, 2026
Adrienne L. Williams-Octalien Director
US VIRGIN ISLANDS
CHANGE
RT Park Solar Farm Ribbon Cutting Ceremony November 2025
BCB Project Launch March 2026

## Slide 2: Get the Funds: Increased Obligations
Year | Obligations
Sep 2025 | $24,000,000,000
Sep 2024 | $17,000,000,000
Sep 2023 | $8,500,000,000
Sep 2022 | $5,800,000,000
Sep 2021 | $4,700,000,000
Sep 2020 | $3,600,000,000

## Slide 3: VISION, MISSION & STRATEGIC PRIORITIES
Vision
To build a resilient Virgin Islands.
Mission
To build a safe, resilient community that transforms and strengthens the Territory’s infrastructure by building robust systems, cultivating stakeholder collaboration and completing recovery projects to better position the
community to thrive.
Get the Funds
Secure the maximum amount of disaster recovery funds required for the Territory to rebuild resiliently.
Spend the Funds
Commence and
conclude projects
within the required timeframe to guarantee timely processing of Disaster Recovery funds.
Spend the Funds Correctly
Ensure projects
executed meet all
applicable programmatic and regulatory requirements and internal audits are conducted.
Strategic Priorities
CoreValues
Solutions- oriented
Transparent
Accountable
Committed
Team- oriented
Progressive

## Slide 4: Projects Completed 1,160
RT Park and Wapa Undergrounding
Territory-wide

## Slide 5: Innovative Solutions: Rebuild USVI
Focus for today's session
Permitting
Procurement
Bundles
Super PMO
Building
materials

## Slide 6: Rebuild USVI
During our last appearance before this body in September 2025, we outlined that the goal for Rebuild USVI is to have all critical projects under contract by the end of 2025. SPMO-managed projects account for $16.4 billion of the recovery effort. So far, 34 of the 38 projects are either under contract or in the contracting phase.

## Slide 7: Construction Activity Compression
  Peak overlap of major construction sectors occurs 2027-2029
  Concurrent execution across four major sectors drives peak labor demand in 2028
  Represents the estimated number of major projects in the active construction phase
Projections are sensitive to weather, labor, and logistics constraints

## Slide 8: Other Priority Projects
Outside of Rebuild USVI, the ODR is tracking an additional 87 projects in construction, with 33 more shovel-ready. Project management teams are advancing their portfolios to meet the mission and are committed to getting projects under contract and into construction.

## Slide 9
Donna M. Christian Christiansen, MD, Health Center
Groundbreaking Ceremony – December 16, 2025
In Construction – Target End Q4 2028

## Slide 10
Donna M. Christian Christiansen, MD, Health Center
Concrete Pour – April 2026
In Construction – Target Q4 2028

## Slide 11: Demolition 2026 - Target End April 2031
Governor Juan F. Luis Hospital and Medical Center Contract Executed

## Slide 12: Proposals Due May 8, 2026
Roy L. Schneider Hospital
Solicitation in Progress

## Slide 13
Morris deCastro Clinic (St. John Mixed Sector Bundle) Contract Awarded
Target Construction Dec. 2026 – Target End Dec. 2028

## Slide 14
Myrah Keating Smith Community Health Center (St. John Mixed Sector Bundle) Contract Awarded
Target Demolition Q4 2026

## Slide 15
Old Mental Health Building (St. Thomas Healthcare Bundle)
Contract Executed
Demo Sept. 2026 – Bundle Target End Date Q3 2029

## Slide 16
Arthur Richards PreK-8 School
In Construction
Target Completion Summer 2026

## Slide 17
Arthur Richards PreK-8 School
In Construction
Target Completion Summer 2026

## Slide 18
Bertha C. Boschulte Middle School
Project Launch Ceremony – March 26, 2026
Target End Date Summer 2030

## Slide 19
Bertha C. Boschulte Middle School
In Construction
Target End Date Summer 2030

## Slide 20
  Construction May 2026 - Target End Summer 2030
Charlotte Amalie High School
Groundbreaking Ceremony April 9, 2026

## Slide 21: Bundle Completion Spring 2030
St. Thomas Education Bundle
Contract Executed

## Slide 22
St. Thomas Education Bundle
Contract Executed
Bundle Completion Spring 2030

## Slide 23
St. Croix Central High School
Groundbreaking Ceremony – April 21, 2026
Target End July 2030

## Slide 24
St. Croix Educational Complex
Contract Executed
Target Construction Summer 2026 – Target End Dec. 2028

## Slide 25: Target Construction Q4 2027 - Target End Date Q2 2030
St. Croix Education Bundle
Contract in Progress

## Slide 26
Julius E. Sprauve PreK-12 School (St. John Mixed Sector Bundle) Contract Awarded
Target Construction Dec. 2026 - Target End Date Dec. 2029

## Slide 27
Completed VI Water and Power Authority Undergrounding Projects
St. Croix: Feeder 9B
St. Thomas: Feeder 5A

## Slide 28: 10,124 Poles Installed Territory-wide
VI Water and Power Authority
Composite Pole Installation

## Slide 29
St. Croix North-Central Horizontal Bundle Contract Executed
In Design – Construction Dec. 2026 - Target End Dec. 2032
Total of 28 miles 34% of St. Croix

## Slide 30
St. Thomas East Horizontal Bundle Contract Executed
In Design – Target Construction Q1 2027
Total of 17 miles 55% of St. Thomas

## Slide 31
122!
CDBG-DR: EnVIsion Tomorrow
HOMES IN CONSTRUCTION
87!
HOMES COMPLETED

## Slide 32: WELCOME HOME – Completed Home on St. John
CDBG-DR: EnVIsion Tomorrow

## Slide 33: Completed Home St. Croix, Frederiksted
CDBG-DR: EnVIsion Tomorrow

## Slide 34
CDBG-DR: EnVIsion Tomorrow
Construction St. Thomas, Annas Retreat

## Slide 35: Contractor Training February 2026
CDBG-DR: EnVIsion Tomorrow

## Slide 36: Ribbon Cutting Dec. 2026
D. Hamilton Jackson
In Construction

## Slide 37: Target End Date June 2027
Donoe Redevelopment
In Construction
 August 2025
January 2026 

## Slide 38: STX Board of Realtors Fair Housing Expo April 11, 2026
CDBG-DR: Own A Lot, Build A Home

## Slide 40: Virgin Islands Housing Authority Central Office Demolition
New Senior Housing at Estate Tutu Target Construction June 2026

## Slide 41: Queen Louise Home for the Aged Contract Executed
Construction March 2027 - Target End Date Summer 2029

## Slide 42: Herbert Grigg Home for the Aged Contract Executed
Construction February 2027 - Target End Date February 2029

## Slide 43
Lindbergh Bay Head Start
In Construction
Completion May 2026

## Slide 44
Minetta Mitchell Head Start
In Construction
Completion May 2026

## Slide 45
Anna’s Hope Head Start
In Construction
Completion May 2026

## Slide 46
Concordia Head Start
In Construction
Completion May 2026

## Slide 47
Bolongo Bay Head Start
In Construction
Completion June 2026

## Slide 48: Target End Date Summer 2027
Charles Seales Fire Station
In Construction

## Slide 49: Target Construction Summer 2026
Lionel “Smut” Richards Smith Bay Ballpark Solicitation in Progress

## Slide 50: Sion Farm Greathouse In Construction
Target End Date Fall 2026

## Slide 51: Office of the Lieutenant Governor Street Addressing Initiative

## Slide 52: Athalie Petersen Public Library In Construction
Target End Date Aug. 2026

## Slide 53: Charles W. Turnbull Library In Construction
Target End Date Sept. 2026

## Slide 54: Enid Baa Public Library In Construction
Target End Date June 2026

## Slide 55
Economic Impact: Critical Projects
The U.S. Virgin Islands collects tax revenues from funded disaster projects based on the contractor’s gross receipts. Economic Impact is measured by revenue from gross receipts, withholding, and excise taxes. Recovery projects also impact other forms of revenue, such as licenses, permits, fees, housing, and spending within the community and economy.
Actuals/ Projections | FY | Expenditures
Actuals | FY 2024 | $355,472,946
Actuals | FY 2025 | $467,173,934
Projections | FY 2026 | $643,586,070
Projections | FY 2027 | $733,978,187
Projections | FY 2028 | $1,500,000,000
Projections | FY 2029 | $2,500,000,000
Projections | FY 2030 | $2,750,000,000

## Slide 56
Recovery job creation requires the in-migration of construction labor
Peak labor reaches ~5,500 in Q2 2028
Peak concurrent construction overlap occurs 2027-2029
Workforce Summary

## Slide 57: Office of Disaster Recovery Communications
Website
www.usviodr.com
Instagram
@USVIODR
Facebook
@ODRUSVI
Youtube
@USVIODR
Twitter X
@USVIODR
LinkedIn
@USVIODR

## Slide 58: THANK YOU
Contact:
Adrienne L. Williams-Octalien
Director of the Office of Disaster Recovery & Governor’s Authorized Representative (GAR) Phone: (340)220-1221
Email: info@usviodr.com